## IPM Planner Sample
| 1 | 2 | 3 | 4
| Product or Practice |  | Rate | Area | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC
|  | Rate | Units | Units | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Cool Season Turf Stress | [51 empty] | 1 | bar: JAN 4; FEB 4 to MAR 1; APR 1; APR 4 to MAY 1; MAY 3 to JUN 2; JUN 4 to JUL 2; JUL 4 to AUG 1; SEP 1 to SEP 2; OCT 1 to OCT 2; NOV 4 to DEC 2; DEC 4
2 | Warm Season Turf Stress | [51 empty] | 2
3 | Tree maintenance | [51 empty] | 3 | bar: JAN 1; FEB 1; OCT 1; NOV 1; DEC 1
4 | Renovation | [51 empty] | 4 | M = 1000 sq ft
5 | Overseeding | [51 empty] | 5 | A = acre
6 | Aeration (D1-5, W-2,3) 5/8" 1x1" | [51 empty] | 6 | oz = ounce | bar: APR 1
7 | Heavy topdressing | [51 empty] | 7 | fl oz = fluid ounce | bar: APR 1
8 | Venting (D1-5) | [51 empty] | 8 | lb = pound | bar: JAN 2; FEB 2; MAR 2; APR 2; MAY 2; JUN 2; JUL 3; AUG 3; SEP 3; OCT 3; NOV 2; DEC 3
9 | Grooming | [51 empty] | 9 | qt = quart | bar: MAY 4; JUN 4; JUL 4; AUG 4; SEP 4; OCT 3
10 | Vertical mow set at bench level 0" | [51 empty] | 10 | gal = gallon | bar: MAY 1; JUN 1; JUL 1; AUG 1; SEP 2; OCT 2
11 | Light topdress | [51 empty] | 11 | bar: JAN 1 to DEC 4
12 | Traffic control | [51 empty] | 12 | bar: JAN 1 to DEC 4
13 | Soil testing | [51 empty] | 13 | bar: MAR 2; NOV 1
14 | 46-0-0 urea | 0.44 | oz | M | [48 empty] | 14 | bar: JAN 1; JAN 3 to JAN 4; FEB 2 to FEB 4; MAR 2 to DEC 3
15 | 0-0-50 | 2 | oz | M | [48 empty] | 15 | bar: JAN 1; FEB 1; MAR 1; APR 1; MAY 1; JUN 1; JUL 1; AUG 1; SEP 1; OCT 1; NOV 1; DEC 1
16 | Monnitor salinity (D1 - 5) | [51 empty] | 16 | bar: APR 1 to OCT 4
17 | Leaching | [51 empty] | 17 | bar: APR 1; MAY 1; JUN 1; JUL 1; AUG 1; AUG 3; SEP 1; OCT 1
18 | Irrigation water testing | [51 empty] | 18 | bar: NOV 1
19 | Irrigation maintenance (W1-4) | [51 empty] | 19 | bar: JAN 1; FEB 1; MAR 1; APR 1; MAY 1; JUN 1; JUL 1; AUG 1; SEP 1; OCT 1; NOV 1; DEC 1
20 | Drainage improvement | [51 empty] | 20 | bar: JAN 4; FEB 4; MAR 4; OCT 4; NOV 4; DEC 4
21 | Hand watering | [51 empty] | 21 | bar: JUL 1 to SEP 4
22 | Aerial photography | [51 empty] | 22 | bar: SEP 2
23 | [52 empty] | 23
24 | Merit 75 WP (I1,2,5) | 0.15 | oz | M | [48 empty] | 24 | bar: MAY 4
25 | Conserve SC (I1,3,4) | 1.2 | fl oz | M | JUL 4: (X); AUG 4: (X); SEP 4: (X); OCT 4: (X) | 25
26 | Orthene TTO 97 (if needed, I1,2,5) | 1.4 | oz | M | SEP 1: (X) | 26
27 | Monitor insects with soap drench (I13,4) | 2 | oz | M | [48 empty] | 27 | bar: JAN 1; JAN 3; FEB 1; FEB 3; MAR 1; MAR 3; APR 1; APR 3; MAY 1; MAY 3; JUN 1; JUN 3; JUL 1; JUL 3; AUG 1; AUG 3; SEP 2; SEP 4; OCT 2; OCT 4; NOV 2; NOV 4; DEC 2; DEC 4
28 | Visual monitoring for all diseases | [51 empty] | 28 | bar: JUN 1 to OCT 4
29 | Banner Maxx (D1-4) | 2 | fl oz | M | [48 empty] | 29 | bar: APR 3; MAY 1; MAY 3; JUN 1; JUN 3; SEP 4; OCT 2
30 | Daconil Ultrex (D2,3,4) | 3.2 | oz | M | [48 empty] | 30 | bar: MAY 2; JUN 2; OCT 1
31 | Insignia (D2,3) | 0.5 | oz | M | [48 empty] | 31 | bar: JUL 2; JUL 4; AUG 4; SEP 2
32 | Cleary's 3336 WP (D2) | 8 | oz | M | [48 empty] | 32 | bar: AUG 2
33 | Chipco Signature (D5) | 2 | oz | M | [48 empty] | 33 | bar: MAY 3; JUN 3; JUL 3; AUG 3; SEP 3
34 | Primo Maxx PGR (D1) | 0.125 | fl oz | M | [48 empty] | 34 | bar: FEB 1; FEB 3; MAR 1; MAR 3; APR 1; APR 3; MAY 1; MAY 3; JUN 1; JUN 3; JUL 1; JUL 3; AUG 1; AUG 3; SEP 1; SEP 3; OCT 1; OCT 3; NOV 1
35 | Proxy (W2) | 5 | fl oz | M | [48 empty] | 35 | bar: FEB 1; MAR 1; APR 1; MAY 1
36 | [52 empty] | 36
37 | [52 empty] | 37
38 | [52 empty] | 38
39 | [52 empty] | 39
40 | [52 empty] | 40
41 | [52 empty] | 41
42 | [52 empty] | 42
43 | [52 empty] | 43
44 | [52 empty] | 44
45 | [52 empty] | 45
46 | [52 empty] | 46
47 | [52 empty] | 47
48 | [52 empty] | 48
49 | [52 empty] | 49
50 | [52 empty] | 50
51 | [52 empty] | 51
52 | [52 empty] | 52
53 | [52 empty] | 53
54 | [52 empty] | 54
55 | [52 empty] | 55
56 | [52 empty] | 56
57 | [52 empty] | 57
58 | [52 empty] | 58
59 | [52 empty] | 59
60 | [52 empty] | 60
61 | [52 empty] | 61
62 | [52 empty] | 62
63 | [52 empty] | 63
64 | [52 empty] | 64
65 | [52 empty] | 65
66 | [52 empty] | 66
67 | [52 empty] | 67
68 | [52 empty] | 68
69 | [52 empty] | 69
70 | [52 empty] | 70
| Management zone: | Poa greens
| Course: | Happy Trails GC |  |  | FEB 4: Completed by:; APR 2: Superintendent; JUL 3: Date:; AUG 2: 2009-11-01; OCT 1: Year Covered:; NOV 2: 2010